## WBS
Work Breakdown Structure - HiringCompass: An AI recruitment assistant that guides hiring teams with evidence-backed assessments, keeping humans in control of every decision.
# | Modules | Features | Tasks | UI/UX (man-hour) | Frontend (man-hour) | Backend (man-hour) | QA (man-hour) | Docs/PM (man-hour) | Total (man-hour) | Total (man-day)
Phase-1
1 | Requirement Understanding, Clarification & Planning |  |  | 0 | 0.4 | 0 | 0 | 23.6 | 24 | 3
1.1 |  | Requirement & Scope Understanding |  | 0 | 0 | 0 | 0 | 8 | 8 | 1
1.1.1 |  |  | Study BID, instructor Q&A and clarify F1–F11 scope, constraints and acceptance criteria | - | - | - | - | 5.2 | 5.2 | 0.65
1.1.2 |  |  | Research recruitment domain and available libraries/services; record assumptions and open decisions | - | - | - | - | 2.8 | 2.8 | 0.35
1.2 |  | Solution Planning |  | 0 | 0.4 | 0 | 0 | 15.6 | 16 | 2
1.2.1 |  |  | Define project name/positioning and high-level multi-agent solution approach | - | - | - | - | 2.8 | 2.8 | 0.35
1.2.2 |  |  | Prepare WBS with estimates, dependencies, sequencing and definition of done | - | - | - | - | 4.4 | 4.4 | 0.55
1.2.3 |  |  | Prepare high-level architecture/workflow and LangGraph/orchestration design | - | - | - | - | 4.4 | 4.4 | 0.55
1.2.4 |  |  | Prepare risk register and finalize technology-stack justification | - | - | - | - | 2.4 | 2.4 | 0.3
1.2.5 |  |  | Initialize GitHub repository, README skeleton, /docs, .gitignore and .env.example | - | 0.4 | - | - | 1.6 | 2 | 0.25
Phase-2
2 | Foundation & Multi-Agent Platform |  |  | 0.8 | 1.6 | 6 | 2.4 | 1.2 | 12 | 1.5
2.1 |  | Project Foundation |  | 0.8 | 1.6 | 3.6 | 1.2 | 0.8 | 8 | 1
2.1.1 |  |  | Set up FastAPI backend, frontend shell, Dockerfile(s), Docker Compose and health endpoint | 0.8 | 1.2 | 1.4 | 0.4 | 0.4 | 4.2 | 0.525
2.1.2 |  |  | Set up relational database, migrations, base domain models and persistent volumes | - | - | 1.4 | 0.4 | 0.4 | 2.2 | 0.275
2.1.3 |  |  | Implement environment configuration, safe error handling, structured logging and upload validation | - | 0.4 | 0.8 | 0.4 | - | 1.6 | 0.2
2.2 |  | Agent Orchestration & Persistence |  | 0 | 0 | 2.4 | 1.2 | 0.4 | 4 | 0.5
2.2.1 |  |  | Create LangGraph base state, orchestrator/subgraph skeleton and typed agent hand-off contracts | - | - | 1.6 | 0.4 | 0.4 | 2.4 | 0.3
2.2.2 |  |  | Configure persistent LangGraph checkpointing and verify workflow resume after restart | - | - | 0.8 | 0.8 | - | 1.6 | 0.2
3 | Job Intelligence & Pre-Interview Screening |  |  | 3.8 | 5.2 | 13.1 | 7.9 | 0 | 30 | 3.75
3.1 |  | Agent A — Job Profile Generation |  | 0.4 | 0.8 | 2.8 | 1.6 | 0 | 5.6 | 0.7
3.1.1 |  |  | Build recruiter chatbot input flow and generate structured job description/profile from recruiter criteria | 0.4 | 0.8 | 1 | 0.4 | - | 2.6 | 0.325
3.1.2 |  |  | Integrate company hiring-knowledge RAG into job-profile generation | - | - | 1 | 0.4 | - | 1.4 | 0.175
|  |  | Job posting to hiring sites | - | - | 0.8 | 0.8 | - | 1.6 | 0.2
3.2 |  | CV Intake & Parsing |  | 0.4 | 0.8 | 2.6 | 1.5 | 0 | 5.3 | 0.6625
3.2.1 |  |  | Implement multi-CV upload, file validation and PDF text extraction | 0.4 | 0.8 | 0.8 | 0.4 | - | 2.4 | 0.3
3.2.2 |  |  | Add OCR fallback when PDF has no usable extractable text; handle OCR failure gracefully | - | - | 0.8 | 0.7 | - | 1.5 | 0.1875
3.2.3 |  |  | Extract and persist structured candidate attributes: education, experience, skills, certifications and projects | - | - | 1 | 0.4 | - | 1.4 | 0.175
3.3 |  | F1 — Screening & Requirement-Based Ranking |  | 0.9 | 2 | 4.1 | 2 | 0 | 9 | 1.125
3.3.1 |  |  | Semantically match CV evidence against mandatory/preferred job requirements | - | 0.4 | 1.5 | 0.4 | - | 2.3 | 0.2875
3.3.2 |  |  | Classify requirements as Met / Partially Met / Unmet with evidence and explanations | 0.4 | 0.4 | 1 | 0.4 | - | 2.2 | 0.275
3.3.3 |  |  | Apply mandatory-requirement gate and preserve clear screened-out reason | 0.4 | 0.4 | 0.8 | 0.4 | - | 2 | 0.25
3.3.4 |  |  | Generate individual suitability and relative candidate ranking with batch progress/status | 0.1 | 0.8 | 0.8 | 0.8 | - | 2.5 | 0.3125
3.4 |  | HITL Screening Gate |  | 0.8 | 0.3 | 0.8 | 0.4 | 0 | 2.3 | 0.2875
3.4.1 |  |  | Implement recruiter approve/reject checkpoint after F1 and persist/resume candidate state | 0.8 | 0.3 | 0.8 | 0.4 | - | 2.3 | 0.2875
3.5 |  | F2 — AI Candidate Scoring |  | 0.8 | 0.8 | 1.8 | 1.9 | 0 | 5.3 | 0.6625
3.5.1 |  |  | Derive job-specific scoring weights from recruiter prompt/job profile and persist the weights | - | - | 0.8 | 0.4 | - | 1.2 | 0.15
3.5.2 |  |  | Score technical skills, relevant experience and qualifications on 0–100 scale | 0.4 | 0.4 | 0.3 | 0.4 | - | 1.5 | 0.1875
3.5.3 |  |  | Generate dimension breakdown, natural-language justification and aggregate score | 0.4 | 0.4 | 0.3 | 0.4 | - | 1.5 | 0.1875
3.5.4 |  |  | Validate pipeline parallelism: approved candidates enter F2 while later CVs remain in F1 | - | - | 0.4 | 0.7 | - | 1.1 | 0.1375
3.6 |  | HITL Interview Selection Gate |  | 0.5 | 0.5 | 1 | 0.5 | 0 | 2.5 | 0.3125
3.6.1 |  |  | Recruiter reviews F1/F2 evidence and scores, selects candidates eligible for interview, and persists the interview-selection decision before F3 | 0.5 | 0.5 | 1 | 0.5 | - | 2.5 | 0.3125
4 | Interview & Real-Time Transcription |  |  | 3.2 | 5.8 | 7.6 | 4.4 | 0 | 21 | 2.625
4.1 |  | F3 — AI-Powered Video Interview |  | 2 | 4.2 | 2.8 | 2.4 | 0 | 11.4 | 1.425
4.1.1 |  |  | Implement interview creation/scheduling, unique join link, candidate/job association and session lifecycle | 0.4 | 0.8 | 0.8 | 0.4 | - | 2.4 | 0.3
4.1.2 |  |  | Integrate existing WebRTC/managed RTC solution for 1-to-1 browser video/audio | 0.8 | 2 | 0.8 | 0.8 | - | 4.4 | 0.55
4.1.3 |  |  | Implement mute, camera toggle, end-call and basic reconnect/network recovery | 0.8 | 1 | 0.4 | 0.8 | - | 3 | 0.375
4.1.4 |  |  | Persist session status, participants and start/end timestamps | - | 0.4 | 0.8 | 0.4 | - | 1.6 | 0.2
4.2 |  | F4 — Real-Time Speech Recognition |  | 1.2 | 1.6 | 4.8 | 2 | 0 | 9.6 | 1.2
4.2.1 |  |  | Stream participant audio to Google Speech-to-Text without permanent raw-media retention | - | 0.4 | 1.6 | 0.4 | - | 2.4 | 0.3
4.2.2 |  |  | Structure transcript by participant role, timestamp and conversational turn | 0.4 | 0.4 | 1.2 | 0.4 | - | 2.4 | 0.3
4.2.3 |  |  | Display live transcript and persist/retrieve it after the interview | 0.8 | 0.8 | 1.2 | 0.4 | - | 3.2 | 0.4
4.2.4 |  |  | Handle silence, overlap and STT/API failure without crashing the interview | - | - | 0.8 | 0.8 | - | 1.6 | 0.2
5 | Interview Intelligence & Assessment |  |  | 2.8 | 3.2 | 11.4 | 3.6 | 0 | 21 | 2.625
5.1 |  | F5 — Q&A Analysis |  | 0.8 | 0.8 | 7.4 | 2 | 0 | 11 | 1.375
5.1.1 |  |  | Segment transcript into questions, answers, follow-ups, clarifications and multi-part responses | - | - | 1.6 | 0.4 | - | 2 | 0.25
5.1.2 |  |  | Filter non-evaluable small talk and map Q&A to specific job requirements | - | - | 1.4 | 0.4 | - | 1.8 | 0.225
5.1.3 |  |  | Build authoritative technical RAG retrieval for factual/technical answer verification | - | - | 1.6 | 0.4 | - | 2 | 0.25
5.1.4 |  |  | Evaluate relevance, factual/technical accuracy, completeness and articulation with transcript evidence | 0.4 | 0.4 | 1.6 | 0.4 | - | 2.8 | 0.35
5.1.5 |  |  | Identify requirements explored and requirements never explored during the interview | 0.4 | 0.4 | 1.2 | 0.4 | - | 2.4 | 0.3
5.2 |  | F6 — Consolidated Candidate Assessment |  | 2 | 2.4 | 4 | 1.6 | 0 | 10 | 1.25
5.2.1 |  |  | Merge F1 screening evidence, F2 scores and F5 interview evidence into consolidated assessment | 0.4 | 0.4 | 1.4 | 0.4 | - | 2.6 | 0.325
5.2.2 |  |  | Generate strengths, weaknesses, evidence gaps and recommended verification areas | 0.4 | 0.4 | 1 | 0.4 | - | 2.2 | 0.275
5.2.3 |  |  | Implement printable/exportable candidate assessment report | 0.4 | 0.8 | 0.8 | 0.4 | - | 2.4 | 0.3
5.2.4 |  |  | Implement side-by-side comparison for candidates applying to the same role | 0.8 | 0.8 | 0.8 | 0.4 | - | 2.8 | 0.35
6 | Innovation Feature |  |  | 1.2 | 1.2 | 5.6 | 2 | 0 | 10 | 1.25
6.1 |  | F11 — CV Integrity & Prompt Injection Shield |  | 1.2 | 1.2 | 5.6 | 2 | 0 | 10 | 1.25
6.1.1 |  |  | Detect hidden/white/tiny text and suspicious PDF formatting using document-level signals | - | - | 1.2 | 0.4 | - | 1.6 | 0.2
6.1.2 |  |  | Detect zero-width/unusual Unicode and common prompt-injection/instruction patterns | - | - | 1.2 | 0.4 | - | 1.6 | 0.2
6.1.3 |  |  | Aggregate integrity signals into Normal / Review Required with explainable evidence | 0.4 | 0.4 | 1.2 | 0.4 | - | 2.4 | 0.3
6.1.4 |  |  | Add F11 HITL approve/reject/quarantine gate before F1 and integrate flag into candidate assessment | 0.8 | 0.8 | 1.2 | 0.4 | - | 3.2 | 0.4
6.1.5 |  |  | Test clean CV and crafted adversarial CVs for final demonstration | - | - | 0.8 | 0.4 | - | 1.2 | 0.15
7 | UI/UX Refinement |  |  | 5.6 | 3.2 | 0 | 1.2 | 0 | 10 | 1.25
7.1 |  | Recruiter & Screening UI |  | 2 | 1 | 0 | 0.4 | 0 | 3.4 | 0.425
7.1.1 |  |  | Refine dashboard, Agent A job creation, batch progress, F1 ranking, HITL and F2 scoring views | 2 | 1 | - | 0.4 | - | 3.4 | 0.425
7.2 |  | Interview UI |  | 2 | 1 | 0 | 0.4 | 0 | 3.4 | 0.425
7.2.1 |  |  | Refine two-video-panel interview workspace, controls, candidate context and live transcript based on reference UI | 2 | 1 | - | 0.4 | - | 3.4 | 0.425
7.3 |  | Assessment UI |  | 1.6 | 1.2 | 0 | 0.4 | 0 | 3.2 | 0.4
7.3.1 |  |  | Refine assessment/comparison screens plus loading, empty, error and basic responsive states | 1.6 | 1.2 | - | 0.4 | - | 3.2 | 0.4
8 | Stretch Feature |  |  | 1.3 | 1.7 | 2.9 | 1.3 | 0.8 | 8 | 1
8.1 |  | F7–F10 — One Bounded Stretch Feature or Complete Core Features |  | 1.3 | 1.7 | 2.9 | 1.3 | 0.8 | 8 | 1
8.1.1 |  |  | Select one stretch feature only after F1–F6 and F11 are stable; define strict one-day scope | - | - | - | - | 0.8 | 0.8 | 0.1
8.1.2 |  |  | Implement selected stretch feature using existing core outputs/components | 0.8 | 1.2 | 2.4 | 0.8 | - | 5.2 | 0.65
8.1.3 |  |  | Integrate, regression-test and prepare stretch demonstration; otherwise use day for core hardening | 0.5 | 0.5 | 0.5 | 0.5 | - | 2 | 0.25
9 | Integration, QA & Release |  |  | 0.4 | 1.2 | 5.9 | 11 | 5.5 | 24 | 3
9.1 |  | Multi-Agent Integration & Reliability |  | 0 | 0.4 | 3.2 | 3 | 0 | 6.6 | 0.825
9.1.1 |  |  | Validate multi-job/multi-candidate orchestration and structured agent-output hand-offs | - | - | 1.2 | 1 | - | 2.2 | 0.275
9.1.2 |  |  | Validate F1/F2 pipeline concurrency, background processing and checkpoint/restart/resume behavior | - | - | 1 | 1.2 | - | 2.2 | 0.275
9.1.3 |  |  | Add/review retry and failure states for LLM, OCR, STT, RAG and RTC dependencies | - | 0.4 | 1 | 0.8 | - | 2.2 | 0.275
9.2 |  | Security, Privacy & Performance |  | 0 | 0 | 1.6 | 2 | 0.5 | 4.1 | 0.5125
9.2.1 |  |  | Review role access, secrets, logs, file validation, candidate deletion and third-party data disclosure | - | - | 0.8 | 1 | 0.5 | 2.3 | 0.2875
9.2.2 |  |  | Run 20-CV performance test; record actual parse/screen/score/rank time and optimize obvious bottlenecks | - | - | 0.8 | 1 | - | 1.8 | 0.225
9.3 |  | End-to-End QA |  | 0 | 0 | 0.3 | 3 | 0 | 3.3 | 0.4125
9.3.1 |  |  | Run complete job → CV → F11 → F1 → HITL → F2 → interview → F4 → F5 → F6 regression | - | - | - | 2 | - | 2 | 0.25
9.3.2 |  |  | Test malformed CV/OCR failure, screened-out candidate, network/STT/API failure and restart scenarios | - | - | 0.3 | 1 | - | 1.3 | 0.1625
9.4 |  | Documentation & Release |  | 0.4 | 0.8 | 0.8 | 3 | 5 | 10 | 1.25
9.4.1 |  |  | Complete README: purpose, setup, configuration, usage, privacy, limitations, third-party services and performance | - | - | - | 0.4 | 1.6 | 2 | 0.25
9.4.2 |  |  | Finalize architecture/LangGraph documentation, F11 rationale and privacy/data-handling note | - | - | - | - | 1.2 | 1.2 | 0.15
9.4.3 |  |  | Fresh-clone clean-machine Docker verification and fix release-blocking setup issues | - | 0.4 | 0.4 | 1 | - | 1.8 | 0.225
9.4.4 |  |  | Prepare anonymized demo material and rehearse 20–30 minute presentation | 0.4 | 0.4 | - | 0.4 | 1.2 | 2.4 | 0.3
9.4.5 |  |  | Final regression, repository hygiene, release tag, submission checklist and contingency fixes | - | - | 0.4 | 1.2 | 1 | 2.6 | 0.325
GRAND TOTAL |  |  |  | 19.1 | 23.5 | 52.5 | 33.8 | 31.1 | 160 | 20
Planning note |  | Phase 1: Days 1-3 = 24 man-hours (3 working days)
Phase2: Days 4–20 = 136 man-hours (17 working days), assuming 8 hours per working day.
Stretch remains capped at 8 man-hours and converts to core hardening if mandatory work is unstable.