## Q&A
# | Feature/Area | Question(EN) | Our Understanding | Answer(EN) | Raised by_Name | Raised date | Answered by_Name | Answer date | Status
1 | Project implementation | Can we use technology stacks other than the ones which were taught to us | From the document, Fastapi and langgraph is mentioned. | Your understanding is correct | Tahmid Akter | 25/09/2026 | Jishnu |  | Open
2 | Github configuration | We need to create a new GitHub account using our BJIT email for this project. Can we add our personal GitHub accounts as collaborators so that we can push our code from home? | We understand that the project repository will be created and maintained under the BJIT email account. We would like to know if our personal GitHub accounts can be added as collaborators so that we can access, add, modify, and push code from our personal GitHub accounts, while the project code and repository remain under the BJIT account. | Yes, personal GitHub accounts can be added as collaborators for development and remote access. However, all project code and commits must be stored and maintained in the designated BJIT GitHub repository. | Kawsar Ahmed kazol | 25/09/2026 | Jishnu |  | Open
3 | F3 - Video Interview | Are we permitted to use third-party CPaaS platforms/libraries (e.g. WebRTC via Twilio) for the video/audio streaming, or is a raw WebRTC implementation expected? | We understand that using managed WebRTC libraries is permitted to ensure stability within the tight 17-day timeframe, as long as the backend logic is handled in Python/FastAPI. | Both options are acceptable. The development team may choose either a third-party CPaaS platform/library or a raw WebRTC implementation, depending on which approach is more suitable and easier to implement. | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
4 | F4 - Transcription & Diarization | For distinguishing speakers, if we implement WebRTC with separate audio tracks for the interviewer and candidate, will this channel separation satisfy the speaker attribution requirement without needing complex AI speaker diarization on a mixed audio track? | We understand that capturing two distinct audio channels (one per participant) is a valid and more reliable approach than running AI diarization on a single merged audio file. | Speaker attribution can be handled using participant-specific metadata, such as Participant ID, User ID, or Role (Interviewer/Candidate), associated with the corresponding audio source or channel. This allows the system to identify who is speaking without requiring AI-based speaker diarization on mixed audio. | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
5 | 7.2 - Security (N9) | Section 4.2 excludes Enterprise authentication. For requirement N9 (Access separation), do we need a backend JWT-based auth system? | We understand that a lightweight authentication mechanism (like JWT or session-based) is required to protect API endpoints, but complex SSO/OAuth is out of scope. | Your understanding is correct | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
6 | F1 - CV Parsing | The BID states scanned/image-heavy documents should "fail safely rather than crash the batch." Is implementing OCR to attempt extraction from scanned PDFs considered in-scope, or should we simply skip them and log an error? | We understand that implementing OCR is out of scope and a "graceful skip + log" is the expected behavior for non-text-based PDFs. | Candidate CV ↓ Is text available? ↙ ↘ YES NO ↓ ↓ Text Extraction OCR ↓ ↓ └──────┬──────┘ ↓ CV Parsing ↓ Requirement Match ↓ Screening Results | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
7 | Video/Audio Storage (F3 & N16) | F3 requires capturing the audio stream, but N16 (Data Minimisation) states "Do not retain raw audio or video beyond what is needed to produce the transcript". Are we required to store the raw video recording at all, or is discarding raw media immediately after transcription the preferred approach? | We assume we only need to process the audio stream in real-time for transcription and should explicitly not store raw video/audio files to comply with privacy rules. | No, the raw audio and video data do not need to be stored. The system will capture the audio/video temporarily for transcription and processing, and the raw media will be discarded after the required transcript has been generated. | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
8 | Real-Time Transcription (F4) | F4 requires transcription with "minimal perceptible lag". Is chunk-based batch processing acceptable or is true WebSocket streaming strictly required ? | We assume chunk-based processing is acceptable as long as the UI updates smoothly and the lag is under 2 seconds, avoiding the complexity of full WebSocket streaming if not necessary. | Google Cloud Speech-to-Text Streaming API can be used to provide near-real-time transcription. The audio can be streamed directly to the API without storing the raw audio/video data. True WebSocket streaming is not necessarily required, as Google’s streaming API can use gRPC to provide continuous transcription with minimal delay. | Kawsar Ahmed kazol | 26/09/2026 | Jishnu |  | Open
| F1 - CV Screening | If a candidate fails a hard requirement, such as having less than the minimum experience, should we reject them, or keep them with a lower score and a warning flag? | They stay in the ranking with the unmet requirement clearly marked, so a human makes the final call. No automatic rejection. | If a candidate does not meet any mandatory (hard) requirement, the candidate should be excluded from the screening results and should not proceed to the next stage. | Mohammad Sadman Shafiq | 26/09/2026 | Jishnu |  | Open
10 | F5 - Interview Q&A Analysis | When we are evaluating candidate's answer to the interview questions, do we only rely on the LLMs internal parametric knowledge, or may we use external knowledge (authoritative documentations) to verify the evaluation through RAG? | We understand that any information will come from interview transcript and CV for that specific candidate. But for the relevance, factual and technical accuracy, completeness and overall quality of articulation external sources may be needed. We want to clarify if such external retrieval is permitted. | The evaluation should use external authoritative documentation through RAG to verify the candidate’s answers. The LLM should not rely solely on its internal parametric knowledge. The RAG-based approach should use approved and authoritative sources as references when evaluating the accuracy and relevance of the candidate’s responses. | Kazi Rafiul Kader | 27/09/2026 | Jishnu |  | Open
11 | 9 | Should the candidate suitability score be based only on the defined criteria such as technical skills, relevant experience, and academic/professional qualifications, or should we also include an ATS-style overall score based on CV–job description matching? | We understand that the minimum scoring dimensions are technical skills, relevant experience, and academic/professional qualifications, with configurable weights. | Both approaches are applicable. The candidate suitability score should consider the defined evaluation criteria, such as technical skills, relevant experience, and academic/professional qualifications, as well as an ATS-style CV–job description matching score. | Joy Biswas | 27/09/2026 | Jishnu |  | Open
12 | AI Services / LLM | If we use paid LLM or speech-to-text APIs for the project, will there be any issue ? Alternatively, would using a local LLM be considered a plus point during evaluation? | We understand that both external paid AI services and local LLMs are permitted. We would like to clarify whether using a local LLM provides any additional evaluation benefit. | Your understanding is correct | Joy Biswas | 27/09/2026 | Jishnu |  | Open
13 | Timeline & Phases | The cover page says 17 working days (1–27 Oct 2026: Phase 1 = 2 days, Phase 2 = 15 days), but Section 9 describes a 20-day plan (Phase 1 = Days 1–3, Phase 2 = Days 4–20) . Which one is authoritative? | We understand the dated version is authoritative: 17 working days, Phase 1 ends on Day 2 , final submission and presentation on 27 Oct. | You have to submit all the documents and code by 27 October. | Joy Biswas | 27/09/2026 | Jishnu |  | Open
14 | Live Demo Setup (F3) | For the live interview demo, can we test it on one computer using two browser tabs (one interviewer, one candidate) on localhost, or do we need two separate computers? | We understand that running two browser tabs on the same computer on localhost is enough for the demonstration. | Yes, your understanding is correct | Md. Shafi Mahmud | 27/09/2026 | Jishnu |  | Close
15 | Data Deletion (N19) | For deleting candidate data, is a backend API endpoint (e.g., DELETE /candidates/{id}) or script enough, or do we must have a delete button in the UI? | A backend API endpoint or script to delete candidate data satisfies the requirement, and a UI button is optional. | Backend API is enough no need any extra delete button on the UI | Md. Shafi Mahmud | 27/09/2026 | Jishnu |  | Close
16 | Q&A Analysis (F5) | Interviews often have casual greetings and small talk. Should our AI filter out this small talk and only grade the real job-related questions and answers? | AI should ignore normal small talk and only evaluate actual technical and behavioral answers. | The entire interview conversation, including greetings, small talk, and job-related discussions, should be transcribed. However, only job-related questions and answers should be considered for candidate evaluation and scoring. | Md. Shafi Mahmud | 27/09/2026 | Jishnu |  | Close
17 | Fairness & Bias (N20) | To avoid bias (like age, gender, or nationality), is telling the LLM prompt to ignore them enough, or do we need to remove them from the CV text using code before scoring? | We understand that instructing the LLM via prompt is acceptable, but removing personal details from the text beforehand is better practice. | There is no need to provide specific instructions to the LLM to ignore age, gender, nationality, or other personal attributes. The candidate evaluation should be based on the defined job-related criteria and qualifications. | Md. Shafi Mahmud | 27/09/2026 | Jishnu |  | Close
18 | Roles and login | Which roles are expected: interviewer and candidate only, or also a separate recruiter/admin role? | Two roles: Recruiter/Interviewer and Candidate. | The system will support two roles only: Interviewer and Candidate. The Interviewer will conduct and manage the interview, while the Candidate will participate in the interview. | Mohammad Sadman Shafiq | 27/09/2026 | Jishnu |  | Open
19 | F1 CV Screening and Require,ent-Based Candidate Ranking | Should F1 ( CV Screening & Requirement-Based Candidate Ranking) rank candidates based on the F2 (AI-Based Candidate Scoring) score, or should F1 use a separate ranking score? | F1 ranking will not use the F2 aggregate score, is will have seperate criteria like no. of met requirements. |  | Mohammad Sadman Shafiq | 27/09/2026 | Jishnu |  | Open
20 | F2 - AI-Based Candidate Scoring | Is there a required score scale (0–100, 0–10, percentage), or is this our choice? | The scale is our choice. We will use 0–100 for each dimension and for the aggregate. | The candidate evaluation score should use a 0–100 scale | Mohammad Sadman Shafiq | 27/09/2026 | Jishnu |  | Open
21 | F7 - Candidate Identification & Real-Time Profile Overview | To identify a candidate using facial or voice recognition, the system needs their face or voice data beforehand. However, our pre-interview process only collects CVs. Should we add a separate step where candidates register their face or voice before the interview, or will this data be provided to us? | For example, if Rahim joins an interview, the system needs his previously registered face or voice to confirm that he is Rahim. We understand that if this data is not provided, we would need to implement a registration process with the candidate's consent. | Face or voice recognition is not required in this phase. Candidate identification will be handled without facial or voice recognition. This functionality can be considered as an enhancement in a future phase. | Miftahul Islam | 27/09/2026 | Jishnu |  | Open
22 | F2 - AI-Based Candidate Scoring | Who sets the weights: the recruiter in the UI or a config file? Should there be default weights? | Weights are set for each job through the UI, with default weights according to our choice like 50% for skills, 30% for experience, and 20% for qualifications. | The AI will determine the weights based on the prompt. | Mohammad Sadman Shafiq | 27/09/2026 | Jishnu |  | Open
23 | CV parsing throgutput (N1- Non functional requirements) | N1 asks us to process 20CVs in a reasonable time. Is there any specific time limnit we must meet? | We understand that the 20 CVs should be parsed, screened, scored and ranked withing 5 minutes. We will measure the time from uplaoding the CV to until the ranking is shown. | Yes definately have a time frame | Md. Abdul Kahhar Siddiki Shan | 27/09/2026 | Jishnu |  | Open
24 | F4- Real-Time Speech Recognition & Trnascirpts | During the speech recognition, there is a chance that the transcription will not be performed in the exact way, and there will be errors in the words. How can we handle this error data. | Speech-to-text can get wrong words. For example, "Kubernetes" can be written as 'Cooper netties". Can the interviewer correct the transcript after the interview? Should the analysis use the corrected versiton in feature 5 for the question and answer analysis? | Google Speecch to Text service is good enough to use it. | Md. Abdul Kahhar Siddiki Shan | 27/09/2026 | Jishnu |  | Open
25 | F6 - Candidate Comparison | When comparing candidates, should the system compare only their scores, or should it also show the evidence from their CVs and interview answers side by side? | We understand that the comparison should remain evidence-based, but we would like to confirm how much detail is expected in the comparison view. | The LLM will determine the candidate’s score based on the interview performance and other defined CV criteria. | Ahsan Rizvi | 27/09/2026 | Jishnu |  | Open
26 | F3 - AI-Powered Video Interview | Section 4.1, F3, and F4 consistently describe the video interview using singular terminology (e.g., "between interviewer and candidate," transcribing "both interviewer and interviewee"). However, the BID does not specify a maximum participant limit per session. Should the system be architected strictly for 1-on-1 interviews (2 participants total), or must it support panel interviews with multiple interviewers in a single session? | Based on the descriptions in Section 4.1, F3, and F4, we understand that the system is primarily intended for a 1-on-1 video interview, consisting of one interviewer and one candidate. For example, a session would have one interviewer conducting the interview with a single candidate, while the system captures and transcribes the conversation between the two participants. The BID does not explicitly define support for multiple interviewers or panel interviews; therefore, we currently understand the scope to be limited to two participants per interview session unless otherwise specified. | For this phase, the system will support 1-on-1 interviews only, with one interviewer and one candidate per session. Panel interviews with multiple interviewers are not required at this stage and can be considered in a future phase. | K.M. Abdullah-Al-Maruf | 27/09/2026 | Jishnu |  | Open
27 | About WBS | Can we adjust the WBS during project execution, or should it remain strictly the same as generated at the beginning? | While the WBS structure—including modules, features, and task descriptions—should remain consistent, the man-days and completion dates can be adjusted. If a task is finished ahead of schedule, the timeline can be updated so we can begin the next module early. | Before Starting WBS must be completed | Chowdhury Muhammed Samiul | 27/09/2026 | Jishnu |  | Open
28 | Authentication | Can we use Firebase for user Authentication? | From the requrirements it is clear that there should be multiple user types, so users need to sign up and sign in. Thus user authentication is required. We would like to confirem if we can use Firebase for user authentication. | You can use Firebase Authenticaiton | Sohail Ahmed | 28/09/2026 | Jishnu
29 | F4 - Speech Recognition | Will the interviews be conducted strictly in English or are we required to handle other languages? | Since English is the most obvious choice perhaps that is enough | English | Kaji Sadman Sakib | 28/09/2026 | Jishnu |  | Open
30 | GitHub Repository / Branching Strategy (G5, G8) | Are we expected to merge completed feature branches into the main/default branch throughout development and use it as the single working reference, or should the default branch should remain empty? | Our understanding is that the default branch should be kept in a working state throughout development, with completed and stable changes merged into it as appropriate. Feature-specific development may be carried out in separate branches, while the default branch should remain usable and represent a working version of the application. The final evaluated state should then be explicitly identified using the required final release tag | In the development time we will decide it. | K.M. Abdullah-Al-Maruf | 28/09/2026 | Jishnu |  | Open
31 | F4 – Timestamping | For transcript timestamps, should timestamps represent elapsed time from the beginning of the interview, or actual clock time? | I think both can be acceptable. If elapsed time beginning from the interview, then it would appear like 00:00, 00:15, 01:32 rather than the actual wall-clock time (e.g., 10:05:32 AM). | Both are acceptable | Md Wahiduzzaman Khan Dip | 28/09/2026 | Jishnu |  | Open
32 | AI Usage Guidelines / Deliverables (Section 13, P1/P2) | Section 13 says that the Software Requirements Specification (SRS) must be prepared without AI support. However, the SRS is not listed in the Phase 1 or Phase 2 deliverables. Shouldn't we prepare and submit a separate SRS document as part of the project? | Our understanding is that, since Section 13 specifically mentions the SRS, it may be expected even though it is not explicitly listed in the deliverable | SRS must submit this is the part of a delivarable items | Shahriar Farhan Karim | 28/09/2026 | Jishnu |  | Open
33 | Testing with Custom CVs | At which phase of the project will we be provided with the Custom CVs? | Perhaps the CVs will be provided at the early stages of development so we can test CV screening | yes you are correct | Kaji Sadman Sakib | 28/09/2026 | Jishnu |  | Open
34 | Network Interruption | If a participant's connection drops briefly during an interview, do we need to reconnect them automatically to the same session, or is it acceptable to end the session after a timeout as long as the transcript captured so far is saved? | My initial thought is that the minimum requirement is that the transcript captured so far is never lost. Automatic reconnection to the same session is a nice-to-have, and ending the session after a timeout (for example, 60 seconds) is acceptable, provided the transcript is saved and the interviewer can start a new session for the same candidate. | Reconnect automatically | Md Wahiduzzaman Khan Dip | 28/09/2026 | Jishnu |  | Open
35 | 5.1 Feature summary | Where will we get the job description from? | Either you provide us the job descripion with the cvs or we make the description based on the cvs | LLM will generate | Sumyea Choudhury | 28/09/2026 | Jishnu |  | Open
36 | Overlapping speech | If both people speak at the same time, should the transcript keep both utterances with overlapping timestamps, or is it acceptable to place them in sequence as long as neither is lost? | My understanding is that, since we plan to capture a separate audio channel for each participant, both utterances should be kept as separate speaker-attributed entries, each with its own start and end timestamps, and overlapping timestamps are acceptable. | You can manage your proposed understanding | Md Wahiduzzaman Khan Dip | 28/09/2026 | Jishnu |  | Open
37 | F1 – Requirement Evidence | When the system marks a requirement as Met, Partially Met, or Unmet, should the evidence shown to the recruiter be the exact CV text supporting that decision, or is an AI-generated explanation sufficient? | We understand that the decision must be traceable to candidate evidence, but we would like to confirm whether the original CV text/snippet must be displayed. | An AI-generated explanation is sufficient to support the requirement assessment. | Md. Mahfuj Hasan | 28/09/2026 | Jishnu |  | Open
38 | Q&A segmentation: | Sometimes an interviewer asks two or three things in a single turn, like "Tell me about your Python experience, and how have you used Docker?" Should we split that into separate question-answer pairs and evaluate each one, or is it okay to treat the whole turn as one combined question with one evaluation? | My understanding is that a multi-part question should ideally be split into separate question-answer pairs, so each part can be mapped to the relevant job requirement and evaluated on its own. I also understand that a combined unit is acceptable when the candidate's answer can't be cleanly separated, as long as the evaluation covers all parts. | Could be seperate questions | Md Wahiduzzaman Khan Dip | 28/09/2026 | Jishnu |  | Open
39 | Deliverable P1.2 / Section 10.1 | should the system generate unique, secure individual interview links per candidate session, or is a single generic session link utilized? | We assume the system will generate unique, candidate-specific session links or tokens tied to each scheduled interview instance to ensure proper association with the candidate record and job profile, as required by Feature F3. | After the candidate selection process is completed, the LLM will generate and send a unique interview link to the selected candidate for the scheduled interview session. | K.M. Abdullah-Al-Maruf | 27/09/2026 | Jishnu |  | Open
40 | F3 – Interview Scheduling | The BID mentions the interview lifecycle as create/schedule/join/conduct/end. Is actual future scheduling with date/time required, or is creating a session and joining it sufficient? | We understand that the lifecycle includes scheduling terminology, but the exact scheduling functionality is not defined. | Future interview scheduling should also be supported. The system should allow the interviewer to create and schedule an interview for a future date and time, after which the interviewer and candidate can join the scheduled session. | Md. Mahfuj Hasan | 28/09/2026 | Jishnu |  | Open
41 | Job Requirement Definition | The requirements mention defining a job requirement profile, but it is not clearly specify whether the system must support multiple job profiles simultaneously. Should the system allow us to create and manage multiple job profiles, or is supporting a single active job profile sufficient for this phase or for overall project completion? | Our understanding is that multiple job profiles may be needed, but since this is not clearly specified, a single active job profile may be sufficient for project completion. | The system should support multiple job profiles. Users should be able to create and manage multiple job requirement profiles, with each profile having its own defined requirements and evaluation criteria. | Shahriar Farhan Karim | 28/09/2026 | Jishnu |  | Open
42 | F5 – Technical Accuracy | For technical interview questions, what should be considered the reference source for determining whether an answer is factually or technically accurate? | We understand that technical accuracy must be evaluated, but the BID does not define a formal reference source or knowledge base. | The LLM will evaluate the interview results when the interviewer requests an evaluation. The evaluation will be based on the interview responses and the defined evaluation criteria. | Md. Mahfuj Hasan | 28/09/2026 | Jishnu |  | Open
43 | Scope 4.1 – Job Post / CV Ingestion | The In-Scope table mentions a Job Post with a contact email for CV submission. Does the platform need to ingest CVs from an email inbox, or is manual upload through the application UI sufficient for this project? | We understand manual upload is the intended mechanism, and the Job Post text is illustrative of business context rather than a requirement for email integration. We want to confirm email ingestion is out of scope. | Both options are acceptable. The system may support CV submission through email inbox integration as well as manual CV upload through the application UI. | Mir Tasrif Ahmed | 28/09/2026 | Jishnu |  | Open
44 | F1 – CV Language | Are CVs expected to be in English only? If a CV is submitted in another language, should the system attempt translation, parse only English sections, or fail gracefully and flag it? | We understand the sample CVs and interviews are English. We want to confirm non-English CVs are out of scope and should be handled with a clear error/flag rather than translation. If the CV is not in the extractable text format then OCR will struggle to handle different language other than english | only englsih | Mir Tasrif Ahmed | 28/09/2026 | Jishnu |  | Open
45 | N26 / LangGraph – State Persistence | For long-running LangGraph workflows (e.g., batch CV screening, post-interview analysis), must the graph state be persisted so a job can resume after an application restart? Or is it acceptable to treat a restart as a job failure—keeping completed results and letting the recruiter re-run the remaining work? | We understand N26 requires final candidate records and results to survive a restart. We assume intermediate LangGraph state does not need to be checkpointed. If the app restarts mid-job, we would mark the job as failed/interrupted, preserve already-completed results, and allow the recruiter to re-trigger the unfinished part. We want to confirm if this is acceptable, or if automatic resumability is required. | The system should persist the state of long-running LangGraph workflows so that the process can resume from where it stopped after an application or system restart. Completed results should be retained, and the system should continue processing the remaining work without requiring the recruiter to re-run the completed tasks. | Mir Tasrif Ahmed | 28/09/2026 | Jishnu |  | Open
46 | f1 - cv screening and requirements based candidate ranking | What is the difference between F1(CV screening and requirement based candidate ranking)candidate ranking and F2(AI Based Candidate Scoring) candidate scoring? Why shouldn't F1 simply rank candidates according to the F2 score? | Both features are dependent on each other, no clear distinction between them | Already given the answer in above | Mahbubur Rahman Rafi | 28/09/2026 | Jishnu |  | Open
47 | f10 - interview quality assessment | In case of an interview assessed as bad(quality), do we reschedule the interview or assess it with a score with bad confidence? | Rescheduling the interview seems to be the right choice | Your understanding is correct | Mahbubur Rahman Rafi | 28/09/2026 | Jishnu |  | Open
48 | f1- Feature Summary | From an earlier answer to a question, I learned that an LLM will generate the job description, and in that case there will be a chatbot to generate that job description. My question is if we have a chatbot in our product, do both the interviewer and candidate get access of the chatbot, or will the chatbot just be used for this specific task and in that case only the interviewer will have access to the chatbot? | Only using chatbot for this use case seems to be the right choice as chatbot was not mentioned anywhere in the BID | In the chatbot window, only the interviewer is visible, while the candidate can see only their own video feed. | Mahbubur Rahman Rafi | 28/09/2026 | Jishnu |  | Open
49 | F6 — Consolidated Candidate Assessment | F6 requires an overall suitability position. Should the report end with an explicit recommendation such as Recommend / Consider / Not Recommend, or only present the component scores and evidence for the hiring manager to decide? | We assume the report will include a suggested recommendation label, clearly marked as decision support, with the final hiring decision left to the human. |  | Imtiaj Hossain Saikat | 29/09/2027 |  |  | Open